## Slide 1
Disciplined Software Engineering Lecture #5
Software Engineering Institute
Carnegie Mellon University
Pittsburgh, PA 15213
Sponsored by the U.S. Department of Defense

## Slide 2
Lecture #5 Overview - Resource and Schedule Planning
Resource and schedule planning overview
The planning process
Resource estimating
Schedule estimating
Earned value tracking

## Slide 3
Why Resource and Schedule Plans Are Needed
Provides a business basis for doing the work
  establishes the price
  sets the schedule
  permits agreement on the work
Establishes a management framework
  defines commitments
  helps groups coordinate their work
  allows status tracking

## Slide 4
Estimating Accuracy
Planning is a skill that must be developed
  the PSP helps to build planning skill
  even simple plans are subject to error
    unforeseen events
    unexpected complications
    just plain mistakes
The best strategy is to plan in detail
  identify the recognized tasks
  estimate based on similar experience
  make judgments on the rest

## Slide 5
An Estimating Error Example
When estimating in parts, the total error is less than the sum of the part errors
  errors tend to balance
  this assumes no common bias
For a 1000 hour job
  with estimating accuracy of + or - 50%
  the total estimate is from 500 to 1500 hours
In 25 parts, each with 50% error
  the total would be 1000 hours as before
  the estimate range is from 900 to 1100 hours

## Slide 6
Combining Individual Errors
In combining individual estimates
  combine the estimated values
  add the estimate variances
With 25 estimates
  each estimate averages 40 hours
  the standard deviation is 50% or 20 hours
  the variance for each is 400
  the variances thus total 10,000
  the combined standard deviation is the square root of the variance, or 100
  the estimate range is thus 900 to 1100 hours

## Slide 9
The Planning Process
Define
Requirements
Produce
Conceptual
Design
Estimate
Size
Estimate
Resources
Produce
Schedule
Develop
Product
Size, Resource
Schedule
Data
Process
Analysis
Resources
Available
Productivity
Database
Size
Database
Product
Delivery
Tracking
Reports

## Slide 10
Planning Development Time
Obtain
historical data
Are there sufficient
data for a regression
calculation?
Calculate historical
productivity in LOC
per hour
Calculate the
hours required
Calculate the shortest and
longest likely times
Are there sufficient estimate
data for a regression
calculation?
Do the regression
calculation on actual
object LOC
and actual hours
Calculate the time
required
Calculate the prediction
interval
Do the regression
calculation on estimated
object LOC and actual
hours
Calculate the time
required
Calculate the prediction
intervals
LOC Size Estimate
No
Yes
No
Yes
Time Estimate
Time Estimate
Time Estimate
Estimating
Choice C
Estimating
Choice B
Estimating
Choice A

## Slide 11
The Resource Planning Process
Start with a size estimate
Identify available data
Use regression when you have 3+ sets of data that correlate.
Use data for estimated LOC to actual hours where available.
Calculate the prediction interval.

## Slide 12
Regression in Resource Planning
The regression method for resource planning
is identical to that used for size estimating.
If multiple estimates are combined from the same data
  combine the parts, i.e, if 3 LOC estimates were made, combine their object LOC as input to one resource estimate
  do the same for the prediction interval

## Slide 13
Example of Combining Resources
Start with 3 estimates
  A - 45 hours + or - 10
  B - 18 hours + or - 5
  C - 85 hours + or - 25
The combined estimate is
  total = 45 + 18 + 85 = 148 hours
  variance = 100 + 25 + 625 = 750
  range = square root of variance = 27.4 hours
  estimate is from 121 to 175 hours

## Slide 14
Using Multiple Proxies
If you have size/hour data for several proxies
  estimate each as before
  combine the total estimates and prediction intervals as just described
Use multiple regression if
  there is a correlation between development time and each proxy
  the proxies do not have separate size/hour data
  multiple regression is covered later

## Slide 15
Resource Estimate Summary
To make a resource estimate
  start with a size estimate
  use the PROBE method
  use your historical size and hours data
  use regression if you have sufficient data
Calculate the prediction intervals
  use the same method as with size estimates
  use the size and hour data

## Slide 16
Schedule Estimating
To make a schedule you need three things
  the estimated direct project hours
  a calendar of available direct hours
  the order in which the tasks will be done
You then need to
  estimate the hours needed for each task
  spread these hours over the calendar of available hours

## Slide 17
Available Direct Hours
Staffing schedule
  new projects are not instantly staffed
  you need a committed staffing plan
Produce a calendar spread of available hours
  at 52 weeks a year and 40 hour weeks - one year = 2080 hours
  with 3 weeks vacation and 10 holidays, one year = 1880 hours (90%)
  with 10% for meetings, 5% for mail, ... one year = 1000 to 1400 hours (50 to 65%)

## Slide 18
The Task Order
The task order must be driven by the development strategy
  you need a conceptual approach
  each task needs completion criteria
  must consider task interdependencies
  also consider cost and cycle time priorities
Determine planned task order
  task order will change with new knowledge
  the initial task order provides a basis for planning

## Slide 19
Produce the Schedule
Estimate the hours for each task
  what portion of total hours have such tasks historically taken?
  will anything unusual affect this project?
  to ensure tasks are not omitted, spread the task time for the entire project
Spread the task hours over the calendar
  identify key project checkpoints
  use a standard format

## Slide 20
Task Planning Template
The PSP task planning template is in Table C47
To start filling out this template
  list the tasks in their expected order of completion
  enter the hours each task is expected to take
  add the hours in the cumulative hours column
At this point, start to prepare the schedule planning template

## Slide 21
Schedule Planning Template
The PSP schedule template is in Table C49
To start filling out this template
  list the calendar dates in the left column
  use days or weeks, depending on project scale
    for days, list every date
    for weeks, use a standard day, say Monday
  list the planned direct project hours to be available that week
  add the hours in the cumulative hours column
  complete the task and schedule templates together

## Slide 22
Completing the Plan
For each task
  find the cumulative hours to complete that task on the task template
  find the week on the schedule template when those hours have first been exceeded
  enter the week’s date in the Date column for that task on the task template
You now have the task schedule

## Slide 23
Schedule Planning Example - 1
Using form C47, start with an estimate of the hours per task
Task Hours Cum. Hrs
  1 2 2
  2 5 7
  3 4 11
  4 7 18
  5 3 21
  6 5 26
  7 6 32
  8 3 35
  9 2 37

## Slide 24
Schedule Planning Example - 2
Using form C49, estimate the direct hours available per day
Day Hours Cum. Hrs
  1 3 3
  2 5 8
  3 5 13
  4 5 18
  5 4 22
  6 6 28
  7 5 33
  8 5 38

## Slide 25
Schedule Planning Example - 3
Enter the task schedule: the day on which the cumulative hours for each task are reached
Task Hours Cum. Hrs Day
  1 2 2 1
  2 5 7 2
  3 4 11 3
  4 7 18 4
  5 3 21 5
  6 5 26 6
  7 6 32 7
  8 3 35 8
  9 2 37 8

## Slide 26
Earned Value
The purpose of earned value is to
  establish a value for each task
  permit progress tracking against the plan
  facilitate tracking even with plan changes
The principles behind earned value are
  it provides a common value for each task
  this value is the percent of total project hours this task is planned to take
  no value is given for partial task completion
  major plan changes require new plans

## Slide 27
Establish the Planned Value
On the task template
  total the project hours
  calculate the % each task is of the total hours
  enter this % as the planned value (PV) for that task
  calculate the cumulative PV for each task
On the schedule template
  enter the cumulative planned value for the tasks to be completed each week

## Slide 28
Schedule Planning Example - 4
Next, produce the planned value (PV), or the % of the total job that each task represents
Task Hours Cum. Hrs Day PV Cum. PV
  1 2 2 1 5.4 5.4
  2 5 7 2 13.5 18.9
  3 4 11 3 10.8 29.7
  4 7 18 4 18.9 48.6
  5 3 21 5 8.1 56.7
  6 5 26 6 13.5 70.2
  7 6 32 7 16.3 86.5
  8 3 35 8 8.1 94.6
  9 2 37 8 5.4 100.0

## Slide 29
Schedule Planning Example - 5
Next, enter the cumulative planned value for each day
Day Hours Cum. Hrs Cum. PV
  1 3 3 5.4
  2 5 8 18.9
  3 5 13 29.7
  4 5 18 48.6
  5 4 22 56.7
  6 6 28 70.2
  7 5 33 86.5
  8 5 38 100.0

## Slide 30
Tracking the Plan
As each task is completed, it earns the planned value
  enter this earned value (EV) for that task
  enter the date of task completion
  add the EV to date in the cumulative EV column
In the schedule template, enter the cumulative EV for each week as it is completed
Track earned value versus planned value by week

## Slide 31
Projecting Project Completion
Assume that the project will continue to earn value at the rate it has in the past.
Extrapolate to project completion by linearly extending the EV line until it reaches 100%.
This is the likely project completion date unless
  the rate of progress can be accelerated
  the work for the remaining tasks can be reduced below the original plan

## Slide 32
Schedule Planning Example - 6
During the project, enter on the task planning template the day each task is completed
Task Hours Cum. Hrs Day PV Cum. PV Done
  1 2 2 1 5.4 5.4 1
  2 5 7 2 13.5 18.9 2
  3 4 11 3 10.8 29.7 4
  4 7 18 4 18.9 48.6 5
  5 3 21 5 8.1 56.7
  6 5 26 6 13.5 70.2
  7 6 32 7 16.3 86.5
  8 3 35 8 8.1 94.6
  9 2 37 8 5.4 100.0

## Slide 33
Schedule Planning Example - 7
Also, enter on the schedule template the earned value for each day
Day Hours Cum. Hrs Cum. PV EV
  1 3 3 5.4 5.4
  2 5 8 18.9 18.9
  3 5 13 29.7 18.9
  4 5 18 48.6 29.7
  5 4 22 56.7 48.6
  6 6 28 70.2
  7 5 33 86.5
  8 5 38 100.0

## Slide 34
Schedule Planning Example - 8
Using the actual EV earned per day of 9.72, enter the EV by day to project completion
Day Hours Cum. Hrs Cum. PV EV Proj. EV
  1 3 3 5.4 5.4 5.4
  2 5 8 18.9 18.9 18.9
  3 5 13 29.7 18.9 18.9
  4 5 18 48.6 29.7 29.7
  5 4 22 56.7 48.6 48.6
  6 6 28 70.2 58.3
  7 5 33 86.5 68.0
  8 5 38 100.0 77.8
  9 87.5
  10 97.2
  11 100.0

## Slide 35
Changing the Plan - 1
For small plan changes, the earned value amounts can be adjusted as follows
  assume the change is a task addition
  estimate the hours for the new task
  determine the new task PV%
  add this amount to the project total
  proportionally reduce the value of every task by the ratio 100/(100 + new task PV)

## Slide 36
Changing the Plan - 2
The plan is still tracked against the original planned value schedule.
By adding a task, the value of all the completed and planned tasks is reduced.
When tasks are deleted, the value of all the completed and planned tasks is increased.
For major plan changes, you must produce a new plan.

## Slide 37
Plan Change Example - 1
To add a task, proportionately reduce the other task PVs so they total 100
Task Hours Cum. Hrs PV Cum. PV Adj. EV Cum. AV
  1 2 2 5.4 5.4 4.8 4.8
  2 5 7 13.5 18.9 11.9 16.7
  3 4 11 10.8 29.7 9.5 26.2
  4 7 18 18.9 48.6 16.7 42.9
  5 3 21 8.1 56.7 7.1 50.0
  6 5 26 13.5 70.2 11.9 61.9
  7 6 32 16.3 86.5 14.3 76.2
  8 3 35 8.1 94.6 7.1 83.3
  9 2 37 5.4 100.0 4.8 88.1
  10 5 42 13.5 113.5 11.9 100.0

## Slide 38
Plan Change Example - 2
Enter the adjusted EV for each completed task but track to the original EV plan
Day Hours Cum. Hrs Cum. PV EV Adj. EV
  1 3 3 5.4 5.4 4.8
  2 5 8 18.9 18.9 16.7
  3 5 13 29.7 18.9 16.7
  4 5 18 48.6 29.7 26.2
  5 4 22 56.7 48.6 42.8
  6 6 28 70.2
  7 5 33 86.5
  8 5 38 100.0

## Slide 39
PSP1.1 Additions
The PSP is augmented to include
  resource estimating: already covered
  schedule estimating: already covered
  a new project plan summary
The project plan summary adds
  the cost performance index
  reuse data

## Slide 40
The Cost Performance Index
The cost performance index (CPI) is
  a measure of the degree to which projects are completed within planned cost
  an index of around 1.0 is most desirable
  an index of more than 1.0 indicates that projects are costing more than planned
  an index of less than 1.0 indicates that projects are costing less than planned
  if the index is much less than 1.0, it indicates overly conservative planning

## Slide 41
Reuse
The reuse measures are % reused and % new reused
A high value of % reused is desirable
  resources are concentrated on developing new products
  resources are not spent on redeveloping existing products.
A high value of % new reused indicates that a high percentage of the new and changed LOC are planned for future reuse.

## Slide 42
Assignment #5
Read Chapter 6
Using PSP1.1, write program 5A to do a numerical integration, using Simpson’s rule.
Use program 5A to calculate the values of the normal distribution integral for three values: from minus infinity to 2.5, to 0.2, and to -1.1.
Follow the program, assignment, and process specifications in Appendices C and D.

## Slide 43
Numerical Integration - 1
In principle, numerical integration treats a function as composed of multiple rectangular areas.
It then adds these areas to produce the integral value.
The trick is to sum these areas so as to minimize the error.

## Slide 44
x(low)
x(high)

## Slide 45
Numerical Integration - 2
The formula for calculating the integral is
Here
  W is the width of the rectangular cells
  F is the value of the function for each x value

## Slide 46
Numerical Integration - 3
To determine the integration limits
  most statistical functions are integrated from minus infinity to some value
  all statistical functions have a total area of 1.0 when integrated from minus to plus infinity
With symmetric functions (the normal and t distributions) the procedure is
  for positive values of x, integrate from 0 to x and add 0.5 to get the answer
  for negative values of x, integrate from 0 to the absolute value of x and subtract from 0.5 to get the answer

## Slide 47
Messages to Remember from Lecture 5 - 1
1 - You can use the PROBE method to estimate
development hours.
2 - This also gives you the likely hourly range
within which the project will be completed.

## Slide 48
Messages to Remember from Lecture 5 - 2
3 - With an accurate estimates you can make an
accurate schedule.
4 - The earned value method helps you to track
progress and project job completion.