## Slide 1
Disciplined Software Engineering Lecture #3
Software Engineering Institute
Carnegie Mellon University
Pittsburgh, PA 15213
Sponsored by the U.S. Department of Defense

## Slide 2
Lecture #3 Overview - Size Estimating - 1
Why estimate size?
Some estimating background
Size estimating principles
Estimating approaches
Estimating proxies

## Slide 3
Why Estimate Size?
To make better plans
  to better size the job
  to divide the job into separable elements
To assist in tracking progress
  can judge when job scope changes
  can better measure the work
Value in this course
  learn estimating methods
  build estimating skills

## Slide 4
Estimating Background
Estimating models in other fields
  large base of history
  in wide use
  generate detailed planning data
  require a size estimate as input
Software size estimating experience
  100% + errors are normal
  few developers make estimates
  fewer still use orderly methods

## Slide 5
Size Estimating Principles - 1
Estimating is an uncertain process.
  no one knows how big the product will be
  the earlier the estimate, the less is known
  estimates can be biased by business and other pressures
Estimating is an intuitive learning process.
  ability improves with experience
  some people will be better at estimating than others

## Slide 6
Estimating is a skill.
  improvement will be gradual
  you may never get very good
The objective, however, is to get consistent.
  you will then understand the variability of your estimates
  you seek an even balance between under and over estimates
Size Estimating Principles - 2

## Slide 9
The principal advantages of using a defined estimating method are
  you have known practices that you can work to improve
  it provides a framework for gathering estimating data
  by using consistent methods and historical data, your estimates will get more consistent
Size Estimating Principles - 3

## Slide 10
Define
Requirements
Produce
Conceptual
Design
Estimate
Size
Estimate
Resources
Produce
Schedule
Develop
Product
Size, Resource
Schedule
Data
Process
Analysis
Resources
Available
Productivity
Database
Size
Database
Product
Delivery
Tracking
Reports
The Size Estimating Framework

## Slide 11
Estimating Approaches
Fuzzy logic
Function points
Standard components
Delphi

## Slide 12
Fuzzy Logic Size Estimating - 1
Gather size data on previously developed programs
Subdivide these data into size categories:
  very large, large, medium, small, very small
  establish size ranges
  include all existing and expected products
Subdivide each range into subcategories

## Slide 13
Fuzzy Logic Size Estimating - 2
Allocate the available data to the categories.
Establish subcategory size ranges.
When estimating a new program, judge which category and subcategory it most closely resembles.

## Slide 14
A Fuzzy Logic Example - 1
You have historical data on 5 programs as follows:
  a file utility of 1,844 LOC
  a file management program of 5,834 LOC
  a personnel record keeping program of 6,845 LOC
  a report generating package of 18,386 LOC
  an inventory management program of 25,943 LOC

## Slide 15
A Fuzzy Logic Example - 2
You thus establish 5 size ranges, as follows
  log(1844) = 3.266
  log(25,943) = 4.414
  the difference is 1.148
  1/4th this difference is 0.287
  the logs of the five ranges are thus spaced 0.287 apart
  the limits or these ranges are at 0.1435 above and below the midpoint of each range

## Slide 16
A Fuzzy Logic Example - 3
The 5 size ranges are thus
  very small - 1,325 to 2,566: file utility
  small - 2,566 to 4970: no members
  medium - 4,970 to 9,626: file management and personnel record program
  large - 9,626 to 18,641: report generator
  very large - 18,641 to 36, 104: inventory management

## Slide 17
A Fuzzy Logic Example - 4
Your new program has the following requirements
  analyze marketing performance by product line
  project the likely sales in each product category
  allocate these sales to marketing regions and time periods
  produce a monthly report of these projections and the actual results

## Slide 18
A Fuzzy Logic Example - 5
In comparing the new program to the historical data you make the following judgments
  it is a substantially more complex application than either the file management or personnel programs
  it is not as complex as the inventory management program
  it appears to have significantly more function than the report package
You conclude that the new program is in the lower end of “very large,” or from 18 to 25 KLOC.

## Slide 19
Fuzzy Logic - Summary
To make a fuzzy logic estimate:
1 - Divide the historical produce size data into size ranges.
2 - Compare the planned product with these prior products.
3 - Based on this comparison, select the size that seems most appropriate for the new product.

## Slide 20
Fuzzy Logic Size Estimating - Advantages
Fuzzy logic estimating
  is based on relevant historical data
  is easy to use
  requires no special tools or training
  provides reasonably good estimates where new work is like prior experience

## Slide 21
Fuzzy Logic Size Estimating - Disadvantages
The disadvantages of fuzzy logic are
  it requires a lot of data
  the estimators must be familiar with the historically developed programs
  it only provides a crude sizing
  it is not useful for new program types
  it is not useful for programs much larger or smaller than the historical data

## Slide 22
Function Point Estimating - 1
A function point is an arbitrary unit
  based on application functions
    inputs, outputs, files, inquiries
  scaled by simple, average, complex
For job complexity:
  adjust a further +/- 35%

## Slide 23
Function Point Estimating - 2
Procedure
  determine numbers of each function type in the application
  judge the scale and complexity of each function
  calculate function point total
  use historical data on development cost per function point to make the estimate
  multiply function points times rate to get the estimate

## Slide 24
A Function Point Example - 1
Your new program has the following requirements
  analyze marketing performance by product line
  project the likely sales in each product category
  allocate these sales to marketing regions and time periods
  produce a monthly report of these projections and the actual results

## Slide 25
A Function Point Example - 2
You first estimate the numbers of raw function points as follows:
  inputs: 12 x 4 = 48
  outputs: 7 x 5 = 35
  inquiries: 0
  logical files: 3 x 10 = 30
  interfaces: 2 x 7 = 14
  total raw function points: 127

## Slide 26
A Function Point Example - 3
You next adjust for influence factors:
  data communication: 4
  on-line data entry: 4
  complex processing: 3
  operational ease: 5
  facilitate change: 5
  total influence factors: 21
Complexity multiplier = 0.65+21x0.01=0.86

## Slide 27
A Function Point Example - 4
The function point total is thus: 127x0.86=109.22
Using historical data on hours per function point, calculate the development time for the project.

## Slide 28
Function Point Advantages
The advantages of function points are:
  they are usable in the earliest requirements phases
  they are independent of programming language, product design, or development style
  there exists a large body of historical data
  it is a well documented method
  there is an active users group

## Slide 29
Function Point Disadvantages
The disadvantages of function points are:
  you cannot directly count an existing product’s function point content
  without historical data, it is difficult to improve estimating skill
  function points do not reflect language, design, or style differences
  function points are designed for estimating commercial data processing applications

## Slide 30
Standard Component Sizing - 1
Establish the principal product size levels
  components, modules, screens, etc.
  determine typical sizes of each level
For a new product:
  determine the component level at which estimation is practical
  estimate how many of those components will likely be in the product
  determine the maximum and minimum numbers possible

## Slide 31
Standard Component Sizing - 2
Calculate the size as the
  number of components of each type
  times typical sizes of each type
  total to give size
Calculate for the maximum, minimum, and likely numbers of components.
Calculate size as:
  {maximum+4*(likely)+minimum}/6

## Slide 32
Standard Component Sizing Example - 1
Your new program has the following requirements:
  analyze marketing performance by product line
  project the likely sales in each product category
  allocate these sales to marketing regions and time periods
  produce a monthly report of these projections and the actual results

## Slide 33
Standard Component Sizing - Example - 2
You have the following historical data on a number of standard components
  data input component: 1,108 LOC
  output component: 675 LOC
  file component: 1,585 LOC
  control component: 2,550 LOC
  computation component: 475 LOC

## Slide 34
Standard Component Sizing - Example - 3
First, estimate the maximum, minimum, and likely numbers of the components like these in the new product
  data input component: 1, 4, 7
  output component: 1, 3, 5
  file component: 2, 4, 8
  control component: 1, 2, 3
  computation component: 1, 3, 7

## Slide 35
Standard Component Sizing - Example - 4
Second, calculate the minimum, likely, and maximum size of the product components
  data input component: 1108, 4432, 7756
  output component: 675, 2025, 3375
  file component: 3170, 6340, 12680
  control component: 2550, 5100, 7650
  computation component: 475, 1425, 3325

## Slide 36
Standard Component Sizing - Example - 5
Third, calculate the minimum, likely, and maximum LOC of the new product
  minimum: 7,978
  likely: 13,616
  maximum: 34,786
The size estimate is then
  LOC = (7978+4*13616+34786)/6 = 16,205 LOC
  the standard deviation is (34786-7978)/6=4468
  the estimate range is: 11,737 to 20,673 LOC

## Slide 37
Standard Component Sizing - Advantages and Disadvantages
Advantages
  based on relevant historical data
  easy to use
  requires no special tools or training
  provides a rough estimate range
Disadvantages
  must use large components early in a project
  limited data on large components

## Slide 38
Delphi Size Estimating
Uses several estimators
  each makes an independent estimate
  each submits estimate to a coordinator
Coordinator
  calculates average estimate
  enters on form: average, other estimates (anonymous), and previous estimate
When reestimates stabilize
  average is the estimate
  range is range of original estimates

## Slide 39
Delphi Example - 1
3 estimators are asked to estimate the product.
Their initial estimates are
  A - 13,800 LOC
  B - 15,700 LOC
  C - 21,000 LOC
The coordinator then
  calculates average estimate as 16,833 LOC
  returns this with their original estimates to the estimators

## Slide 40
Delphi Example - 2
The estimators then meet and discuss the estimates.
Their second estimates are
  A - 18,500 LOC
  B - 19,500 LOC
  C - 20,000 LOC
The coordinator then
  calculates average estimate as 19,333 LOC
  asks the estimators if they agree with this as the estimate

## Slide 41
Delphi Size Estimating - 2
Advantages
  can produce very accurate results
  utilizes organization’s skills
  can work for any sized product
Disadvantages
  relies on a few experts
  is time consuming
  is subject to common biases

## Slide 42
Size Estimating Proxies - 1
The basic issue
  good size measures are detailed
  early estimators rarely can think in detail
Alternatives
  wait to estimate until you have the detail
  make your best guess
  identify a suitable proxy

## Slide 43
Size Estimating Proxies - 2
A good proxy should correlate closely to development costs.
A good proxy would be easy to visualize early in development.
It should also be a physical entity that can be counted.

## Slide 44
Example Proxies
Function points
Objects
Product elements
  components
  screens, reports, scripts, files
  book chapters

## Slide 45
Function Points as Proxies - 1
Data show that function point counts correlate well with development time.
Function points can be visualized early in development.
To use function points properly, trained estimators are required.

## Slide 46
Function Points as Proxies - 2
Function points cannot directly be counted.
Conversion factors are available for counting LOC and calculating function points from the LOC value.
The function point users group (IFPUG) is refining the function point method.

## Slide 47
Standard Components as Proxies
Component count correlation with development depends on the components.
A lot of development data is required.
Component counts are hard to visualize early in development.
Components are machine countable.

## Slide 48
Objects as Proxies - 1
Correlation with development hours
  numbers of objects correlate reasonably well
  object lines of code (LOC) correlate very closely
  object LOC can be estimated using the standard component estimating method
  then calculate LOC estimate from historical relationship between object LOC and program LOC

## Slide 49
Objects as Proxies - 2
When objects are selected as application entities, they can be visualized early in development.
Functions and procedures can often be estimated in the same way.
Objects, functions, procedures, and their LOC can be automatically counted.

## Slide 50
Object LOC Correlation With Development Hours

## Slide 51
Example Proxies - Other
Possible candidates
  screens, reports, scripts, files
  book chapters
If the number of items correlates with development, you estimate the number of items.
With a suitable proxy size measure, you can often estimate proxy size.

## Slide 52
Chapter Pages vs. Time

## Slide 53
Next Lecture - Estimating Software Size - 2
The PROBE estimating method
Statistical estimating considerations
A size estimating example
Estimating considerations

## Slide 54
Assignment #3 - 1
Read chapter 5
Using PSP0.1, write program 3A
  count object or function LOC in a program
  produce the name, LOC count, and method count for each object
  produce the total program LOC count
  you may enhance program 2A to make program 3A (but keep a copy of 2A)

## Slide 55
Assignment #3 - 2
Use program 3A to count programs 1A, 2A, and 3A and report the results in the test report.
Produce a report on the defect fix times for programs 1A, 2A, and 3A.
Refer to the program and assignment specifications in Appendices C and D.

## Slide 56
Messages to Remember from Lecture 3
1 - Accurate size estimates will help you to
make better development plans.
2 - Size estimating skill improves with practice.
3 - A defined and measured process provides a
repeatable basis for improvement.
4 - There are several ways to make size
estimates.